## Budget vs actual
Construction cost tracker
Project
Site
Start date
Updated | 2026-10-09
Code | Cost item | Budget (excl GST) | Approved variations | Revised budget | Committed (quotes, orders) | Invoiced to date | Paid to date | Forecast final | Variance to revised budget | % of revised budget spent | Notes
01 | Preliminaries and site set-up
02 | Consent, design, engineering and council fees
03 | Demolition and site works
04 | Foundations and slab
05 | Framing
06 | Roofing
07 | Cladding and flashings
08 | Windows and exterior doors
09 | Plumbing and drainage
10 | Electrical
11 | Insulation and linings
12 | Interior joinery and doors
13 | Painting
14 | Flooring and tiling
15 | Kitchen and bathrooms
16 | Heating and ventilation
17 | Decks, landscaping, driveway
18 | Contingency
TOTAL
Forecast final cost vs original budget
Contingency remaining
Shaded cells are inputs. Variations, invoiced and paid pull from the other sheets by cost code. Forecast final is the larger of revised budget, committed and invoiced; overwrite it where you know better. Negative variance turns red.

## Variations
Variation no. | Description | Requested by | Date approved (blank = not approved) | Approved amount (excl GST) | Cost code | Time impact (days)
Only approved variations (with a date) should carry an amount; the budget sheet sums column E by cost code. Use the variation approval form in this library for the signature.

## Invoices
Date | Supplier or subcontractor | Cost code | Invoice or claim no. | Amount (excl GST) | Due date | Paid (amount) | Paid on | Payment claim under the CCA?

## How to use
How to use this tracker
1. Budget vs actual: enter the budget per cost code (column C) from the quote, and committed amounts (column F) as quotes are accepted and orders placed. Delete codes you do not need; add rows inside the table and copy the formulas down.
2. Variations: log every change the day it is raised. Put an amount only once it is approved and dated. The budget sheet adds it to the right cost code.
3. Invoices: one line per invoice or payment claim, with the cost code. Due dates in the past that are not fully paid turn red. Tick whether a claim is a payment claim under the Construction Contracts Act 2002: those must be paid or answered with a payment schedule within the contract's period (20 working days by default) or the amount becomes a debt.
4. Forecast final is the larger of revised budget, committed and invoiced. If you know a trade will come in over, type the number over the formula.
5. Update weekly, and send the client the Budget vs actual sheet with every progress claim. Over-budget conversations are easy at 10% and impossible at 40%.
Why this exists
Across 13,567 publicly posted reviews of NZ builders and outdoor and civil construction contractors, value is the lowest-scoring of the four rated dimensions (97.6 out of 100) and quote accuracy is praised in only 13 to 14% of positive reviews. Projects rarely go over budget in one jump; they go over one unlogged variation at a time.
Free to use and adapt for your own business. ClearLogic Intelligence, clearlogicintelligence.com/resources/