CLEARLOGIC INTELLIGENCE  |  CERTIFICATE TEMPLATE · CONSTRUCTION

Practical completion certificate

Issued when the work is complete except for minor defects that do not stop the client using it. Who issues it is set by your contract: usually the contractor gives notice and the client, or the architect or engineer named in the contract, confirms and signs.

Project: ____________________________________________

Site address: ____________________________________________

Contract reference and date: ____________________________________________

Contractor: ____________________________________________

Client (owner): ____________________________________________

Contract administrator, if any (architect, engineer, project manager): ____________________________________________

1. Certification

The contractor gave notice on ______________ that the works had reached practical completion. Having inspected the works on ______________, the [client / contract administrator] certifies that the works reached practical completion on ______________, except for the defects and omissions listed in the attached schedule.

☐  All inspections required by the building consent have been passed, or are listed below as outstanding

☐  The site has been cleaned and the contractor's plant removed, except as listed

☐  Keys, codes and remotes handed over: ______________

☐  Documents in section 3 handed over or dated below

2. Consequences under the contract

| Item | Detail |
| --- | --- |
| Defects liability period | ____ months from the date above; the contractor fixes defects notified in writing in that period |
| Retentions and final claim | ____% released on practical completion, balance at the end of the defects period; final payment claim issued on or after this date under the Construction Contracts Act 2002 |
| Risk and insurance | Responsibility for the works passes to the client on this date; the client's building and contents insurance should be in place from now |

3. Documents handed over (owner-builder work of $30,000 or more: required by s 362T of the Building Act 2004 and reg 9)

☐  Current insurance policies covering the work; guarantees and warranties for materials and services, whether they transfer and how to claim

☐  Maintenance information needed to meet the Building Code and keep warranties valid

☐  Records of work (Form 6A) from every Licensed Building Practitioner who did or supervised restricted building work (s 88): ____ of ____ received; electrical, gas and plumbing certificates

☐  Code compliance certificate applied for on ______________ (council decides within 20 working days of a complete application; apply within 2 years of the consent, ss 92 to 95)

For the client / contract administrator (name, signature): ____________________________________________

Date: ____________________________________________

For the contractor (name, signature): ____________________________________________

Date: ____________________________________________

Not legal advice; the contract wording governs. Building Act references checked on legislation.govt.nz and building.govt.nz on 9 October 2026.

ClearLogic Intelligence  |  clearlogicintelligence.com/resources/  |  Free to use and adapt for your own business  |  2026

CLEARLOGIC INTELLIGENCE  |  SCHEDULE · CONSTRUCTION

Defects and omissions schedule

Attached to the practical completion certificate. Every line has an owner and a date; nothing is 'to be sorted'.

Project: ____________________________________________

Date of walk-through: ____________________________________________

Present: ____________________________________________

Schedule number: ____________________________________________

| # | Location | Defect or omission | Agreed fix | By (date) | Fixed on | Client initial |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |

A defect is work that does not meet the contract or the Building Code. Scuffs and marks from normal use after handover are not. If the parties disagree on a line, write both views and the contract's dispute clause decides.

ClearLogic Intelligence  |  clearlogicintelligence.com/resources/  |  Free to use and adapt for your own business  |  2026

CLEARLOGIC INTELLIGENCE  |  CHECKLIST · CONSTRUCTION

Pre-handover building inspection checklist

Walk the job the day before the client does. Mark each item OK, defect (add to the schedule) or N/A.

| Area | Check | OK / defect / NA |
| --- | --- | --- |
| Exterior | Cladding complete, flashings and sealant continuous, penetrations sealed, no damage |  |
| Roof and gutters | Roofing fixed, flashings, gutters and downpipes clear and connected, no debris |  |
| Joinery | Every window and door opens, closes, locks; glazing undamaged; seals and hardware fitted |  |
| Decks, steps, balustrades | Fixed, level, barrier heights and gaps to code |  |
| Site | Ground falls away from the building, paths, driveway, drainage grates, fences, letterbox; site clean |  |
| Interior linings | Walls and ceilings stopped, sanded, painted; no cracks, nail pops or mismatched sheen |  |
| Floors | Flooring laid, edges finished, no squeaks or lifting, transitions tidy |  |
| Kitchen | Cabinetry aligned, doors and drawers run, benchtop sealed, appliances installed and tested |  |
| Bathrooms and laundry | Tiles and grout sound, waterproofing penetrations sealed, fixtures run and drain, hot water at taps, no leaks under vanities |  |
| Plumbing | All taps, toilets, hot water cylinder, gas appliances tested; no drips |  |
| Electrical | Every light, switch, power point and appliance tested; switchboard labelled; smoke alarms fitted and working; certificates issued |  |
| Heating, ventilation | Heat pump or heating runs; extract fans vent outside; ducting connected |  |
| Doors and hardware | Internal doors hung, latch and swing clear; handles, stops and locks fitted |  |
| Finishing | Paint touch-ups done, protective film removed, labels off, silicone tidy |  |
| Documents | Manuals, warranties, keys, certificates, records of work collected for section 3 of the certificate |  |

Across 13,567 publicly posted reviews of NZ builders and outdoor and civil construction contractors, clear explanation is praised in 34 to 41% of positive reviews and a follow-up after the job in only about 2%. The handover meeting is where the explanation happens; the follow-up visit, booked for a month later, is the thing almost nobody does.

ClearLogic Intelligence  |  clearlogicintelligence.com/resources/  |  Free to use and adapt for your own business  |  2026