## Schedule of works
Schedule of works
Project: |  |  | Site: |  |  | Prepared: | 2026-10-07
Working days per week: | 5
# | Stage | Task | Trade / subcontractor | Start | Finish | Working days | Depends on (#) | Status | % done | Notes
1 | Pre-start | Consent issued and conditions read | Office | 2026-10-12 |  | 5 |  | Not started | 0%
2 | Pre-start | Site set-out, fencing, toilet, power | Builder |  |  | 5 | 1 | Not started | 0%
3 | Site works | Excavation and drainage | Earthworks / drainlayer |  |  | 5 | 2 | Not started | 0%
4 | Site works | Foundations and slab | Concrete |  |  | 5 | 3 | Not started | 0%
5 | Structure | Floor framing (if suspended) | Builder |  |  | 5 | 4 | Not started | 0%
6 | Structure | Wall framing | Builder |  |  | 5 | 5 | Not started | 0%
7 | Structure | Roof trusses and roofing | Builder / roofer |  |  | 5 | 6 | Not started | 0%
8 | Lock-up | Building wrap, windows and doors | Builder / joiner |  |  | 5 | 7 | Not started | 0%
9 | Lock-up | Cladding | Builder / cladder |  |  | 5 | 8 | Not started | 0%
10 | Services | Plumbing rough-in | Plumber |  |  | 5 | 9 | Not started | 0%
11 | Services | Electrical rough-in | Electrician |  |  | 5 | 10 | Not started | 0%
12 | Services | Pre-line inspection | Council |  |  | 5 | 11 | Not started | 0%
13 | Interior | Insulation and linings | Builder / GIB stopper |  |  | 5 | 12 | Not started | 0%
14 | Interior | Interior joinery and doors | Builder |  |  | 5 | 13 | Not started | 0%
15 | Interior | Painting | Painter |  |  | 5 | 14 | Not started | 0%
16 | Finishing | Tiling, flooring | Tiler / flooring |  |  | 5 | 15 | Not started | 0%
17 | Finishing | Kitchen and bathroom fit-off | Plumber / electrician |  |  | 5 | 16 | Not started | 0%
18 | Finishing | Decks, landscaping, driveway | Civil / landscaper |  |  | 5 | 17 | Not started | 0%
19 | Completion | Defects and final clean | Builder |  |  | 5 | 18 | Not started | 0%
20 | Completion | Code compliance certificate | Council |  |  | 5 | 19 | Not started | 0%
21 | Completion | Handover and follow-up visit booked | Builder |  |  | 5 | 20 | Not started | 0%
Estimated completion
Total working days (sum of rows)
Formulas:
Finish = WORKDAY([Start],[Prepared:]-1)
Start = WORKDAY([Finish, row above],1)

## Trades and contacts
Trade | Company | Contact | Phone | Email | Booked for stages (#) | Lead time (days) | Notes

## How to use
How to use this schedule
1. Put the real start date in the first Start cell (E6). Every other date calculates from it using working days, Monday to Friday.
2. Change Working days for each task. Finish dates and the estimated completion move automatically.
3. Tasks run one after the other by default (each starts the working day after the previous one finishes). To run two tasks in parallel, type a date into Start for the second task instead of leaving the formula.
4. Update Status each week. Finish dates in the past that are not Done turn red.
5. Add stages by inserting rows inside the table. Copy the formulas in Start and Finish down.
6. Share the file, or a PDF of the Schedule sheet, with the client at the pre-construction meeting and every time a date moves. A schedule only the builder can see is not a schedule.
Why this exists
Across 13,567 public reviews of NZ builders and outdoor and civil construction contractors, punctuality is one of the most-praised traits (38 to 40% of positive reviews). What customers notice is not one late day but the next stage inheriting the delay without anyone telling them. This sheet is the telling.
Free to use and adapt for your own business. ClearLogic Intelligence, clearlogicintelligence.com/resources/